## Sheet1
Section | Task | Priority | Owner | Details
Images list/Gallery | Render images for selection | 1 | 1 | DONE
Core | Draw image to canvas | 1 | 1 | DONE
Core | Support single text line (but prepare for more) | 1 | 1 | DONE
Core | Support going back to list | 1 | 1 | DONE
Editor | Increase / decrease font size | 1 | 2
Editor | Text color | 1 | 2 | DONE
Core | Download button | 2 | 2
Core | Navigation (Desktop/Mobile) | 2 | 2
Images list | Filter images list by search box | 2 | 2
Editor | Text shadow (on/off) | 1 | 2
Editor | Support adding multiple lines ("add line" button) | 2 | 2
Images list | Filter images list by popular-keyword | 3 | 2
Editor | Align left, right, center | 3
Editor | Select font | 3
Editor | Move lines up/down/left/right with buttons | 3
Editor | Delete line | 3
Home | About us | 3
| Animations: When switching between list and editor, slide right / left | 4
| When submitting the contact-us - open the gmail complete link | 4
| Animations: while filtering the list | 4
| Upload from device / camera | 5
| Hexagons | 5 |  | DONE
| Share on Facebook | 5
Core | Allow switching the UI to hebrew | 5
| Animations: When hovering an image zoom-in | 5